## Product Backlog
Project Name | Study Planner
Client | Academic Institution / Self
Scrum Master | Amdadul
Developers | Friend 1 (Dev/Tester) ¦ Friend 2 (Dev/Tester)
Creation Date | DD-MM-YYYY
Approval Date | DD-MM-YYYY
Epic | User Story ID | Feature / Title | User Story | Status | Acceptance Criteria
SP_Epic_001 : User Authentication & Account Management — The app delivers value only when a student can securely register, log in, and manage their account. | US001 | User Registration | As a new user, I want to register with my email and password, So that I can create my personal study planner account. | New | Email must be unique; password min 8 chars; verification email sent on signup.
| US002 | User Login & Logout | As a registered user, I want to log in and log out securely, So that my data stays private. | New | Session must expire after 30 mins of inactivity; logout clears session token.
| US003 | Password Reset | As a user who forgot my password, I want to reset it via email link, So that I can regain access to my account. | New | Reset link valid for 1 hour only; old password invalidated immediately on reset.
SP_Epic_002 : Subject & Session Management — Core value is delivered when a student can add subjects and log study sessions against them. | US004 | Add / Edit / Delete Subjects | As a student, I want to add, edit, and delete subjects, So that I can organise my study areas. | New | Subject name must be unique per user; delete must warn if active sessions exist.
| US005 | Log a Study Session | As a student, I want to log a study session with subject, date, and duration, So that I can track time spent on each subject. | New | Duration must be > 0 mins; date cannot be in the future; session links to an existing subject.
| US006 | Edit / Delete a Session | As a student, I want to edit or delete a logged session, So that I can correct mistakes. | New | Only the session owner can edit/delete; changes must be reflected immediately on dashboard.
SP_Epic_003 : Dashboard & Goal Tracking — Value is realised when a student can see a daily summary, set weekly goals, and monitor progress with visual bars. | US007 | Daily Dashboard | As a student, I want a dashboard showing today's study hours and total per subject, So that I can monitor my daily effort. | New | Dashboard refreshes on login; shows today's total and cumulative totals per subject.
| US008 | Weekly Goal Setting | As a student, I want to set a weekly study-hour goal per subject, So that I stay on track with academic targets. | New | Goal must be a positive number; system shows actual vs goal variance in hours.
| US009 | Progress Bars per Subject | As a student, I want visual progress bars showing % of weekly goal achieved, So that I can quickly see how close I am to my target. | New | Bar updates in real time as sessions are logged; turns green when 100% reached.
SP_Epic_004 : Productivity Tools — Engagement increases when a student can use a to-do list, study streak counter, and quick notes within the planner. | US010 | To-Do List per Subject | As a student, I want to maintain a to-do list for each subject, So that I can track tasks and mark them complete. | New | Tasks must be addable, editable, and deletable; completed tasks visually struck through.
| US011 | Study Streak Counter | As a student, I want to see my consecutive study-day streak, So that I am motivated to study every day. | New | Streak increments if ≥1 session logged per day; resets to 0 if a day is missed.
| US012 | Quick Notes per Subject | As a student, I want to write and save quick notes for each subject, So that I can jot down important points without leaving the planner. | New | Notes auto-save on typing; plain text; 2000-character limit per subject.
SP_Epic_005 : History, Calendar View & Admin Panel — Complete visibility is achieved when a student can browse study history on a calendar and an admin can monitor all users. | US013 | Calendar View of Study History | As a student, I want a calendar highlighting days I studied and total hours per day, So that I can identify gaps in my routine. | New | Studied days highlighted; clicking a day shows session details; supports month navigation.
| US014 | Study History Report | As a student, I want to filter and view my study sessions by date range or subject, So that I can review my performance over time. | New | Filter by subject and date range; show total hours and session count in the results.
| US015 | Admin Panel | As an admin, I want to view all registered users and their activity, So that I can monitor platform usage and support users. | New | Admin role required; displays username, registration date, last login, and total session count.

## Sprint Planning
Sprint | User Story ID | Feature / Title | Assigned To | Story Points | Start Date | End Date | Status
Sprint 1 | US001 | User Registration | Friend 1 (Dev/Tester) | 5 | DD-MM-YYYY | DD-MM-YYYY | Planned
Sprint 1 | US002 | User Login & Logout | Friend 2 (Dev/Tester) | 3 | DD-MM-YYYY | DD-MM-YYYY | Planned
Sprint 1 | US003 | Password Reset | Friend 1 (Dev/Tester) | 3 | DD-MM-YYYY | DD-MM-YYYY | Planned
Sprint 2 | US004 | Add / Edit / Delete Subjects | Friend 2 (Dev/Tester) | 3 | DD-MM-YYYY | DD-MM-YYYY | Planned
Sprint 2 | US005 | Log a Study Session | Friend 1 (Dev/Tester) | 5 | DD-MM-YYYY | DD-MM-YYYY | Planned
Sprint 2 | US006 | Edit / Delete a Session | Friend 2 (Dev/Tester) | 3 | DD-MM-YYYY | DD-MM-YYYY | Planned
Sprint 3 | US007 | Daily Dashboard | Friend 1 (Dev/Tester) | 5 | DD-MM-YYYY | DD-MM-YYYY | Planned
Sprint 3 | US008 | Weekly Goal Setting | Friend 2 (Dev/Tester) | 3 | DD-MM-YYYY | DD-MM-YYYY | Planned
Sprint 3 | US009 | Progress Bars per Subject | Friend 1 (Dev/Tester) | 5 | DD-MM-YYYY | DD-MM-YYYY | Planned
Sprint 4 | US010 | To-Do List per Subject | Friend 2 (Dev/Tester) | 3 | DD-MM-YYYY | DD-MM-YYYY | Planned
Sprint 4 | US011 | Study Streak Counter | Friend 1 (Dev/Tester) | 3 | DD-MM-YYYY | DD-MM-YYYY | Planned
Sprint 4 | US012 | Quick Notes per Subject | Friend 2 (Dev/Tester) | 3 | DD-MM-YYYY | DD-MM-YYYY | Planned
Sprint 5 | US013 | Calendar View of Study History | Friend 1 (Dev/Tester) | 5 | DD-MM-YYYY | DD-MM-YYYY | Planned
Sprint 5 | US014 | Study History Report | Friend 2 (Dev/Tester) | 3 | DD-MM-YYYY | DD-MM-YYYY | Planned
Sprint 5 | US015 | Admin Panel | Friend 1 (Dev/Tester) | 5 | DD-MM-YYYY | DD-MM-YYYY | Planned
Total Story Points

## Tasks
Developer Tasks |  | QA / Tester Tasks
1 | Understanding Requirements | 1 | Understanding Requirements
2 | System Design & Architecture | 2 | Writing Test Scenarios
3 | Database Schema Design | 3 | Writing Test Cases
4 | Frontend UI Development | 4 | Test Case Reviews
5 | Backend / API Development | 5 | Test Data Preparation
6 | Unit Testing | 6 | Test Environment Setup
7 | Integration Testing | 7 | Functional Test Execution
8 | Code Review | 8 | Re-Testing Bugs
9 | Bug Fixes | 9 | Regression Testing
10 | DevOps / Deployment Setup | 10 | Cross-browser / Mobile Testing
11 | Team / Sprint Meetings | 11 | Team / Sprint Meetings
12 | Any other… | 12 | Automation
|  | 13 | Any other…